## Sheet1
Project Charter
Project Title |  | ChargeLinK |  |  | Project Manager |  | Dhruv Ranjan
Project Start Date |  | 2023-06-03 |  |  | Project End Date
Business Needs
Live Data Integration and the real time display of data of the Stations.
Project Scope |  |  |  |  | Deliverables
The website show all nearby electric vehicle charging sations. |  |  |  |  | The person can directly navigate and book slot from us.
Financials
NA
Milestone Schedule
Milestone |  |  | Target Completion Date |  |  | Actual Completion Date
Planning | Done |  | 2023-06-01 |  |  | 2023-06-03
Frontend | In Progress |  | Basic Frontend |  |  | Basic Frontend
2023-08-20
Backend | In Progress |  | Basic Backend with minimal requirements | Backend with more Features |  | Basic Backend with minimal requirements |  | Backend with more Features
|  |  | 2023-08-25 | 2023-09-25
Survey | Done |  | Form Creation | Form 1 & Form 2 Survey Responses |  | Form Creation |  | Form 1 & Form 2 Survey Responses
|  |  | 2023-07-20 | 2023-07-31 |  | 2023-07-21 |  | 2023-07-31